Maptifier — Production-Grade Phase Roadmap

Executive Summary

Maptifier is a real-time Android projection mapping app targeting buttery-smooth 60 fps on mid-range hardware. It enables users to import media, warp/mask content onto surfaces via touch, draw live, mix dual channels, and output clean visuals to an external projector — all from a phone, no laptop required.

The project spans 9 phases over 12–14 calendar weeks with a team of 4–5 Unity devs, 1 designer, and QA. The MVP (Phases 0–5, weeks 1–8) delivers external display output, core warping/masking, drawing, dual-layer mixing, effects, and project save/load. The remaining phases (6–8, weeks 9–14) add polish, optimization, device certification, and Play Store release prep.

The highest-risk areas are USB-C/DisplayPort alt-mode fragmentation across Android OEMs, sustained GPU performance during dual-layer + effects compositing, and achieving fluid drawing feel across varying touch digitizers. Each is addressed with specific mitigations below.

1. Project Overview and Non-Goals

Project Goals

- Ship a production Android app (Android 10+, optimized for 14+) that is the easiest pocket projection mapping tool available

- Clean external display output via USB-C HDMI / DisplayPort alt-mode (primary) and wireless Cast/Miracast (fallback)

- Real-time touch-based 4-corner and mesh warping, polygon/brush masking

- Fluid pressure/velocity-simulated drawing engine

- Dual independent layers with live crossfade mixing

- 5–8+ real-time GPU effects (kaleidoscope, tunnel, color morph, distortion, etc.)

- 60 fps sustained on Snapdragon 7xx/8xx-class devices during complex scenes

- Dark, minimal, large-touch-target UI

Non-Goals (Explicitly Out of Scope)

- iOS support — Android only for v1; iOS can be evaluated post-launch

- Desktop/laptop companion app — the phone IS the control surface

- Multi-device sync — no networked multi-phone projection

- 3D projection mapping — 2D surface mapping only (planar surfaces)

- Audio-reactive features — no beat detection or audio input in v1 (candidate for v2)

- Cloud storage / accounts — local-only project storage; no login, no cloud sync

- AR/camera-based auto-calibration — manual corner-pin only; AR calibration is a v2 candidate

- Streaming output (NDI, RTMP, etc.) — external display only

- Custom user plugin/shader system — built-in effects only

- Tablet-specific layouts — phone-first; tablets work but no dedicated UI

2. High-Level Architecture

graph TB

subgraph phoneDisplay ["Phone Display (Private Control UI)"]

UIToolkit["UI Toolkit Layer<br/>Touch Controls, Timeline,<br/>Layer Panel, Effects"]

InputSystem["New Input System<br/>Touch, Gesture, Pressure"]

end

subgraph coreEngine ["Core Engine"]

ProjectMgr["Project Manager<br/>JSON + Addressables"]

LayerMixer["Layer Mixer<br/>Dual Channel Crossfade"]

WarpEngine["Warp Engine<br/>4-Corner + Mesh Grid"]

MaskEngine["Mask Engine<br/>Polygon + Brush"]

DrawEngine["Drawing Engine<br/>Pressure/Velocity Sim"]

EffectsPipeline["Effects Pipeline<br/>Shader Graph + Custom"]

MediaPipeline["Media Pipeline<br/>VideoPlayer + RenderTexture"]

end

subgraph renderPipeline ["URP Render Pipeline"]

LayerA_RT["Layer A RenderTexture"]

LayerB_RT["Layer B RenderTexture"]

CompositRT["Composite RenderTexture"]

WarpMesh["Warp Mesh Renderer"]

end

subgraph externalOut ["External Display Output"]

DisplayMgr["DisplayManager<br/>Android Presentation"]

ExtSurface["Projector Surface<br/>Clean Output Only"]

end

subgraph storage ["Storage"]

JSONProj["JSON Project Files"]

Thumbnails["Thumbnail Cache"]

MediaCache["Imported Media Cache"]

ExportMgr["Export Manager<br/>Video Clip Recorder"]

end

InputSystem --> WarpEngine

InputSystem --> MaskEngine

InputSystem --> DrawEngine

UIToolkit --> LayerMixer

UIToolkit --> EffectsPipeline

UIToolkit --> ProjectMgr

MediaPipeline --> LayerA_RT

MediaPipeline --> LayerB_RT

DrawEngine --> LayerA_RT

DrawEngine --> LayerB_RT

LayerA_RT --> EffectsPipeline

LayerB_RT --> EffectsPipeline

EffectsPipeline --> LayerMixer

LayerMixer --> CompositRT

CompositRT --> WarpMesh

WarpMesh --> ExtSurface

WarpMesh --> UIToolkit

DisplayMgr --> ExtSurface

ProjectMgr --> JSONProj

ProjectMgr --> Thumbnails

CompositRT --> ExportMgr

ExportMgr --> MediaCache

Key Architectural Decisions

- Dual RenderTexture pipeline: Each layer renders to its own RT; the mixer blends them into a composite RT. This keeps layer operations independent and GPU-efficient.

- Warp mesh is geometry, not pixel shader: Corner-pin and mesh warping deform a subdivided quad mesh (vertex manipulation), not per-pixel UV distortion. This is dramatically cheaper on mobile GPUs.

- Effects are post-process on layer RTs: Each effect is a blit pass on the layer's RT before mixing. Chain is kept short (max 2–3 effects per layer) for performance budget.

- Android Presentation class for external display: The composite RT is rendered to a secondary Surface via android.app.Presentation on a DisplayManager-detected display. This ensures no UI leaks to the projector.

- UI Toolkit over uGUI: Better performance, styling via USS, and future-proof with Unity 6 direction.

Rendering Budget (per frame at 60 fps = 16.6 ms)

| Component | Budget |
| --- | --- |
| Input processing + game logic | 2 ms |
| Media decode (VideoPlayer) | 2 ms (async) |
| Drawing stroke update | 1 ms |
| Effect passes (2–3 per layer) | 4 ms |
| Layer compositing + mix | 2 ms |
| Warp mesh render | 1 ms |
| External display blit | 1 ms |
| UI render (phone only) | 2 ms |
| Headroom | 1.6 ms |

3. Detailed Phased Roadmap

Phase 0: Project Setup and Spikes (Week 1)

Goal: Establish project foundation, validate highest-risk technical assumptions, align the team.

Duration: 1 calendar week

Key Deliverables:

- Unity 6 LTS project with URP configured for Android, committed to GitHub with Git LFS

- Working CI pipeline (GitHub Actions) building debug APKs

- Spike results for: external display output, video-to-RenderTexture, and touch drawing latency

- Coding standards document, branching strategy, and Jira board populated

Success Metrics:

- Debug APK builds and installs on 3+ test devices

- External display spike shows content on a connected monitor/projector

- Video spike plays a test clip to a RenderTexture at 30+ fps

- Drawing spike captures touch input and renders strokes at 60 fps

Dependencies and Prerequisites:

- Unity 6 LTS installed on all dev machines (Hub license)

- At least 3 Android test devices available (1x flagship, 1x mid-range, 1x budget-ish)

- USB-C to HDMI adapter + test projector or external monitor

- GitHub org/repo created, team access configured

- Jira project created

Detailed Task Breakdown:

Core Dev (Lead):

- Create Unity 6 LTS project, configure URP, set Android build target (SDK 29 min, SDK 34 target)

- Configure Player Settings: IL2CPP, ARM64, Vulkan primary / OpenGL ES 3.2 fallback, linear color space

- Set up Git repo with .gitignore (Unity-standard), Git LFS tracking for *.png, *.jpg, *.mp4, *.fbx, *.asset, *.shader

- Configure GitHub Actions CI: build debug APK on push to develop, artifact upload

- Establish folder structure:

Assets/

_Project/

Scripts/

Core/

Display/

Drawing/

Effects/

Input/

Layers/

Masking/

Media/

Projects/

UI/

Warping/

Shaders/

Materials/

Prefabs/

UI/

Resources/

Addressables/

Plugins/

Android/

- Write coding standards doc (naming, architecture patterns — lean MVC, ScriptableObject events, no singletons except ServiceLocator)

- Set up assembly definitions for each module (compile time optimization)

Core Dev (Spike — External Display):

- Write Android Java/Kotlin plugin using Presentation class + DisplayManager

- Create Unity C# bridge (NativeDisplayBridge.cs) that detects external displays and sends a RenderTexture to the external surface

- Test with USB-C HDMI adapter on Samsung Galaxy S23, Pixel 7, and one Xiaomi device

- Document: detection latency, supported resolutions, vsync behavior, what happens on disconnect

- Key gotcha: Samsung DeX mode intercepts external display — must detect and handle or disable DeX-style windowing

Graphics Dev (Spike — Video Pipeline):

- Set up VideoPlayer component playing a test 1080p H.264 MP4 to a RenderTexture

- Measure decode latency, frame rate, memory usage on mid-range device

- Test: seek, loop, pause/resume, switching clips

- Validate RenderTexture format (ARGB32 vs R8G8B8A8_UNorm) for downstream compositing

Graphics Dev (Spike — Drawing Latency):

- Implement minimal touch → Catmull-Rom spline → GL.Begin/End immediate-mode rendering

- Measure touch-to-photon latency (target: under 30 ms perceived)

- Test EnhancedTouch from new Input System for multi-touch and pressure data availability

- Key gotcha: Not all Android devices report pressure; some report 0 or 1.0 only. Must have fallback velocity-based simulation.

UI/UX Designer:

- Deliver initial style guide: color palette (dark theme, navy/cyan/magenta accent from logo), typography (system sans-serif for perf), spacing/grid system

- Wireframe the primary screens: Canvas View, Layer Panel, Effects Drawer, Project List

- Define touch target sizes (minimum 48dp per Material Design, prefer 56dp for gloved/dark-room use)

QA:

- Set up device matrix spreadsheet (OEM, model, SoC, Android version, USB-C alt-mode support, screen size)

- Install debug APKs from CI, validate install/launch on all test devices

- Set up crash reporting (Firebase Crashlytics) and basic analytics (Firebase Analytics) SDKs

Edge Cases and Device Considerations:

- Samsung DeX: intercepts HDMI as desktop mode; need to detect via Configuration.uiMode and either disable DeX or use DeX-aware Presentation

- Xiaomi MIUI: aggressive battery optimization kills background services; must request battery optimization exemption

- Pixel devices with Tensor chips: Vulkan driver quirks — validate early

- Some USB-C cables are charge-only (no alt-mode); app should show clear "no display detected" messaging

Phase 1: Infrastructure and External Display (Weeks 2–3)

Goal: Production-quality external display pipeline, input system foundation, base rendering loop.

Duration: 2 calendar weeks

Key Deliverables:

- Robust external display detection, connection, resolution negotiation, and clean output

- Hot-plug support (connect/disconnect at any time without crash)

- Base URP rendering loop: single RenderTexture displayed on both phone preview and external display

- Input system foundation with gesture recognizer (tap, drag, pinch, two-finger rotate)

- Base UI shell (dark theme, bottom nav, canvas area)

Success Metrics:

- External display connects and shows content within 2 seconds of cable plug-in

- Hot-plug 20 times without crash or leak

- Preview on phone matches external output (aspect-ratio corrected)

- Gesture system correctly differentiates tap/drag/pinch/rotate with zero false triggers

- Frame rate: 60 fps with static RenderTexture output

Dependencies: Phase 0 complete; spike results reviewed

Detailed Task Breakdown:

Core Dev (External Display — Production):

- Refactor spike code into production DisplayService:

  - IDisplayService interface with events: OnDisplayConnected, OnDisplayDisconnected, OnResolutionChanged

  - AndroidDisplayService implementation using DisplayManager.DisplayListener

  - EditorDisplayService mock for in-editor testing (renders to a second Game view)

- Implement resolution negotiation: query supported modes via Display.getSupportedModes(), prefer highest refresh rate at native resolution, fallback to 1080p

- Handle display lifecycle:

  - Cable disconnect during render: gracefully release Surface, null-check RT, fire event

  - App backgrounding with display connected: pause rendering to external (Android will reclaim resources)

  - App resume: re-detect display, reconnect

  - Display resolution change (e.g., switching TV input): re-create Presentation at new resolution

- Implement vsync strategy: external display may run at different refresh rate than phone; use Application.targetFrameRate = 60 and QualitySettings.vSyncCount = 0 (manual vsync via frame timing)

- Critical: Use SurfaceTexture or Surface from Android side, blit composite RT via Graphics.Blit in OnRenderImage or custom URP pass

Core Dev (Input System):

- Configure New Input System with EnhancedTouch enabled

- Build InputService:

  - Raw touch tracking (up to 10 simultaneous touches)

  - Gesture recognizer state machine: Idle → Tap / Drag / Pinch / Rotate

  - Gesture events: OnTap(pos), OnDragStart/Move/End(pos, delta), OnPinch(center, scale), OnRotate(center, angle)

  - Coordinate system: screen-space → canvas-space transformer (accounts for canvas zoom/pan)

- Implement canvas viewport: pan (two-finger drag), zoom (pinch), with inertia and bounds clamping

- Key gotcha: Unity's EnhancedTouch must be explicitly enabled via EnhancedTouchSupport.Enable() — forgetting this is a common bug

Graphics Dev (Base Render Loop):

- Create CompositeRenderer:

  - Allocates composite RenderTexture (match external display resolution, ARGB32, no depth for final composite)

  - Renders a test color/image to composite RT

  - Blits composite RT to phone preview (aspect-ratio letterboxed) AND to external display surface

- Implement RenderTexturePool: reusable RT allocation to avoid GC pressure from RT create/destroy

- Set up URP Renderer with custom render passes via ScriptableRendererFeature:

  - CompositePass: blits layer RTs through mixer into composite RT

  - ExternalDisplayPass: copies composite RT to external surface

UI/UX (Shell):

- Implement base UI Toolkit layout:

  - Top bar: project name, settings gear, display status indicator (green dot = connected, red = disconnected)

  - Center: canvas preview area (touch-interactive)

  - Bottom: tool bar (Select, Warp, Mask, Draw, Effects) with large 56dp icons

  - Right drawer: layer panel (collapsed by default)

- Implement dark theme USS stylesheet matching style guide

- Display connection status with real-time indicator and toast notifications ("Projector connected — 1920x1080 @ 60Hz")

QA:

- Test external display on all devices in matrix with at least 3 different HDMI adapters

- Stress test hot-plug (rapid connect/disconnect)

- Test with: HDMI adapter, USB-C hub, wireless dongle (note: wireless is Phase 7, but baseline detection test now)

- Log and report resolution negotiation results per device/adapter combo

- Verify no UI elements appear on external display

Edge Cases:

- USB-C hub with multiple displays: only use first detected display, ignore others

- 4K external display: cap at 1080p for performance, allow user override in settings

- Phone screen off while projecting: must keep rendering to external display (use WakeLock + FLAG_KEEP_SCREEN_ON)

- Split-screen / picture-in-picture: disable external display output in these modes to avoid conflicts

Phase 2: Core Mapping Engine (Weeks 4–5)

Goal: Ship the core value proposition — touch-based warping and masking of imported media on surfaces.

Duration: 2 calendar weeks

Key Deliverables:

- Photo/video import from Android gallery via system picker

- 4-corner perspective warp with draggable corner handles

- Basic mesh warp (4x4 grid with draggable control points)

- Polygon mask (tap-to-place vertices, close shape, invert)

- Brush mask (freehand paint-to-reveal/paint-to-hide)

- All transforms output correctly to external display

Success Metrics:

- Import a 1080p photo and 1080p video, warp each, see result on projector within 10 seconds of import

- 4-corner warp: drag any corner, preview updates at 60 fps, output matches preview

- Mesh warp (16 control points): drag points smoothly, no tearing, 60 fps

- Polygon mask: create 8+ vertex polygon, mask applies in real time

- Brush mask: paint mask at 60 fps with no visible latency

Dependencies: Phase 1 complete (display pipeline, input system, base render loop)

Detailed Task Breakdown:

Core Dev (Media Import):

- Implement MediaImportService:

  - Launch Android ACTION_PICK or ACTION_GET_CONTENT intent for images and video

  - Handle content:// URI resolution, copy to app-local storage (avoid permission revocation issues)

  - Supported formats: JPEG, PNG, WebP (images); MP4 H.264, VP9 (video)

  - Generate thumbnail on import (256x256) for project browser

- Implement MediaSource abstraction:

  - ImageSource: loads texture via Texture2D.LoadImage (async via UnityWebRequestTexture for large files)

  - VideoSource: configures VideoPlayer, outputs to dedicated RenderTexture

  - Both implement IMediaSource { RenderTexture OutputRT; bool IsReady; }

- Key gotcha: Android scoped storage (SDK 30+) requires READ_MEDIA_IMAGES and READ_MEDIA_VIDEO permissions, NOT READ_EXTERNAL_STORAGE. Must handle permission request flow with rationale dialog.

Graphics Dev (Warp Engine):

- Implement WarpMesh:

  - Subdivided quad mesh (configurable resolution: 2x2 for 4-corner, up to 16x16 for smooth mesh warp)

  - UV mapping: identity (0,0)→(1,1), maps source RT onto mesh

  - Vertex positions stored in NativeArray<float3> for Burst-compatible manipulation

- Implement FourCornerWarp:

  - 4 draggable handles at corners

  - Bilinear interpolation of interior vertices from corner positions (perspective-correct requires homogeneous coords)

  - Important: True perspective warp requires a projective texture mapping shader, not just bilinear vertex interpolation. Implement via custom shader that computes per-pixel UV from homogeneous coordinates.

- Implement MeshWarp:

  - NxM grid of control points (default 4x4)

  - Catmull-Rom or B-spline interpolation between control points for smooth deformation

  - Vertex buffer updated via Mesh.SetVertices with MeshUpdateFlags.DontRecalculateBounds for performance

- Implement warp handle UI:

  - Circular drag handles (20dp radius) at control points

  - Highlight active handle, show guide lines

  - Snap-to-grid option (toggle)

  - Undo/redo stack for warp changes (Command pattern)

Graphics Dev (Mask Engine):

- Implement MaskRenderer:

  - Renders mask to a single-channel RenderTexture (R8 format, same resolution as layer RT)

  - Mask RT is multiplied with layer RT in the composite shader (output.a *= mask.r)

- Implement PolygonMask:

  - User taps to place vertices; double-tap or "close" button to complete polygon

  - Polygon rendered to mask RT via GL.Begin(GL.TRIANGLES) with ear-clipping triangulation

  - Support for multiple polygons (additive or subtractive)

  - Invert mode (mask everything outside polygon)

- Implement BrushMask:

  - Stamp-based rendering: place brush texture stamps along touch path

  - Adjustable radius (pinch while in brush mode) and hardness (slider)

  - Render stamps to mask RT using additive blending

  - Eraser mode: render stamps with BlendOp RevSub to remove mask

- Both mask types must be serializable for project save

UI/UX:

- Warp mode UI: show/hide control point handles, corner vs. mesh mode toggle

- Mask mode UI: polygon tool, brush tool, radius slider, hardness slider, invert toggle, clear button

- Tool switching: bottom bar highlights active tool, shows relevant sub-options

- Import button: floating action button or menu item, launches gallery picker

QA:

- Test import with: tiny images (16x16), huge images (8K), corrupt files, DRM-protected video, various codecs

- Test warp with: extreme corner positions (overlapping corners, very thin trapezoids)

- Test mask with: very complex polygons (50+ vertices), rapid brush painting

- Memory profiling: import 10+ high-res images, check for leaks

- Test on devices with different aspect ratios (16:9, 20:9, foldables)

Edge Cases:

- Video with non-square pixels: force square pixel interpretation

- Rotated images (EXIF orientation): read EXIF and pre-rotate

- Very large images (8K+): downscale to max 4096x4096 on import (mobile GPU texture size limit)

- Import during active external display: must not cause frame drop on projector

- Warp mesh with degenerate triangles (crossed control points): clamp to prevent inverted triangles

Phase 3: Creative Tools — Drawing and Effects (Weeks 6–7)

Goal: Deliver the creative expression layer — fluid drawing and a rich initial effects library.

Duration: 2 calendar weeks

Key Deliverables:

- Fluid real-time drawing engine with pressure/velocity simulation

- Color picker, brush size, opacity controls

- 5–8 real-time GPU effects: kaleidoscope, tunnel, color cycle/morph, wave distortion, pixelate, edge glow, chromatic aberration, blur

- Effect parameter UI with live preview

- Effects apply per-layer before mixing

Success Metrics:

- Drawing feels fluid and responsive (under 20 ms touch-to-pixel latency) on mid-range devices

- Stroke rendering is smooth (no visible segmentation) at fast swipe speeds

- Each effect runs at 60 fps individually on mid-range device

- 2 effects stacked per layer still maintains 60 fps on mid-range device

- Effect parameter changes preview in real time with no stutter

Dependencies: Phase 2 complete (layer RT pipeline, mask system for brush reference)

Detailed Task Breakdown:

Graphics Dev (Drawing Engine):

- Implement DrawingCanvas:

  - Dedicated RenderTexture per layer for drawing (same resolution as layer RT)

  - Drawing RT composited with media RT: finalLayerRT = mediaRT * maskRT + drawingRT * drawMaskRT

- Implement stroke rendering pipeline:

  - Capture touch points at input rate (may exceed 60 Hz on some devices via EnhancedTouch)

  - Fit Catmull-Rom spline through recent points (4-point window)

  - Subdivide spline into segments (adaptive: more segments for curves, fewer for straight)

  - For each segment, stamp brush texture with interpolated size/opacity

  - Size modulated by: base size * pressure * velocity curve

  - Opacity modulated by: base opacity * pressure

- Implement pressure simulation for devices without pressure data:

  - Infer "pressure" from velocity: fast = thin/light, slow = thick/heavy (inverse mapping, user-adjustable curve)

  - Use Touch.radius where available as secondary signal

- Brush rendering:

  - Soft round brush (Gaussian falloff texture, 64x64 or 128x128)

  - Hard round brush (binary circle)

  - Render via Graphics.DrawTexture or custom blit shader with proper alpha blending

  - Critical: Use premultiplied alpha to avoid dark fringing at stroke edges

- Implement undo/redo:

  - Snapshot drawing RT to a ring buffer (last 20 states)

  - Use RenderTexture.GetTemporary for snapshots, compress to Texture2D + EncodeToJPG for memory efficiency

  - Optimization: Store diffs (XOR of before/after) for lower memory usage if full snapshots are too expensive

- Clear canvas, eraser tool (draw with destination alpha = 0)

Graphics Dev (Effects Pipeline):

- Implement EffectPipeline:

  - Ordered list of IEffect per layer

  - Each effect: takes input RT, produces output RT (ping-pong between two temp RTs)

  - Max 3 effects per layer (hard limit for performance)

  - Effects processed BEFORE layer mixing

- Implement effects as Shader Graph + fallback hand-written shaders:

  - Kaleidoscope: Convert UV to polar, modulo angle by (2*PI/segments), mirror alternating segments. Params: segment count (2–32), rotation, center offset.

  - Tunnel / Zoom: Polar UV + animated radius offset. Creates infinite-zoom-in effect. Params: speed, center, twist amount.

  - Color Cycle / Morph: Shift hue over time in HSV space. Params: speed, hue range, saturation boost.

  - Wave Distortion: Sinusoidal UV displacement. uv.x += sin(uv.y * freq + time) * amp. Params: frequency, amplitude, speed, direction.

  - Pixelate: Quantize UV to grid. uv = floor(uv * pixelCount) / pixelCount. Params: pixel size, shape (square/hex).

  - Edge Glow: Sobel edge detection + glow color overlay. Params: threshold, glow color, glow width.

  - Chromatic Aberration: Offset R/G/B channels in UV space. Params: intensity, direction (radial/linear).

  - Blur: Dual Kawase blur (mobile-efficient alternative to Gaussian). Params: radius (1–8 pixels, using 2–4 downsample passes).

- Shader optimization techniques for mobile:

  - Use half precision everywhere except UV coordinates

  - Minimize texture samples (each is expensive on mobile)

  - Avoid branching in fragment shaders; use step/lerp instead

  - Dual Kawase blur instead of Gaussian (2x fewer samples)

  - Use [HideInInspector] for internal shader props to reduce SetPass overhead

  - Mark all effect shaders with "RenderPipeline" = "UniversalPipeline" tag

UI/UX:

- Drawing toolbar: brush type selector, color picker (HSV wheel + recent colors strip), size slider (with preview circle), opacity slider

- Color picker: compact HSV wheel that expands on tap, eye-dropper tool (tap canvas to sample)

- Effects panel: scrollable grid of effect thumbnails with live-preview icons, tap to add to current layer

- Effect parameter UI: each active effect shows as a card with sliders for its parameters, drag to reorder, swipe to remove

- Real-time preview: parameter changes apply immediately (no "apply" button)

QA:

- Drawing latency measurement: high-speed camera recording of touch + screen response

- Effect performance profiling: each effect solo, then combinations (2x, 3x stacked)

- Test drawing with: stylus (Samsung S Pen), finger, fast swipes, slow precise strokes, multi-touch drawing

- Test effects with: 4K media source, video source (effects on moving content), extreme parameter values

- Memory profiling: undo stack memory usage with 20 drawing states

Edge Cases:

- Drawing while video is playing: drawing RT composites on top, video keeps playing underneath

- Very fast stroke that skips pixels: adaptive subdivision must fill gaps (check segment length vs. brush size)

- Effect on video with alpha regions: effects should respect alpha, not fill transparent areas

- Multiple effects + drawing + video simultaneously: must stay within GPU budget (profile and enforce limits)

- Samsung S Pen: reports true pressure values 0.0–1.0; prefer these over velocity simulation when available

Phase 4: Layers, Mixing and Performance (Weeks 8–9)

Goal: Dual-layer system with live crossfade mixing, performance optimization to sustain 60 fps under full load.

Duration: 1.5 calendar weeks

Key Deliverables:

- Two independent layers (A/B), each with own media, warp, mask, drawing, effects

- Live crossfade slider (A←→B) with multiple blend modes

- Layer solo/mute, opacity control

- Performance optimization pass: GPU instancing, texture atlasing, shader variant stripping

- Frame budget monitoring and adaptive quality system

Success Metrics:

- Both layers active with media + 1 effect each: 60 fps on mid-range device

- Crossfade slider produces smooth, real-time blend with no stutter

- Memory usage under 512 MB total with both layers fully loaded

- No GC spikes greater than 2 ms during mixing operations

- Adaptive quality system drops gracefully (reduces effect quality before dropping frames)

Dependencies: Phases 2 and 3 complete

Detailed Task Breakdown:

Core Dev (Layer System):

- Implement LayerManager:

  - Manages two Layer instances (A and B)

  - Each Layer owns: MediaSource, WarpMesh, MaskRenderer, DrawingCanvas, EffectPipeline, RenderTexture outputRT

  - Layer rendering is sequential: render Layer A → render Layer B → mix → composite → external display

- Implement LayerMixer:

  - Crossfade: output = lerp(layerA, layerB, mixValue) where mixValue 0.0 = full A, 1.0 = full B

  - Blend modes (custom shader): Normal, Additive, Multiply, Screen, Overlay, Difference

  - Blend mode and mix value controlled by UI slider + mode picker

  - Mixer runs as a single blit pass (very cheap)

- Layer controls: solo (show only this layer), mute (hide this layer), opacity (per-layer alpha multiplier)

Graphics Dev (Performance Optimization):

- Shader variant stripping: Audit URP shader variants, strip unused ones (fog, lightmaps, etc.) — can reduce build size by 50+ MB and improve load times

- RenderTexture management: Audit all RT allocations, ensure proper release, use RenderTexture.GetTemporary/ReleaseTemporary for transient RTs

- Draw call optimization: Batch UI elements, minimize material switches, use MaterialPropertyBlock instead of material instances for per-object properties

- GC elimination:

  - Audit all per-frame allocations using Unity Profiler

  - Replace string concatenation with StringBuilder or Span<char>

  - Use NativeArray / NativeList for all hot-path collections

  - Cache component references, avoid GetComponent in Update loops

  - Use stackalloc for small temporary arrays

- GPU profiling: Use Mali Offline Compiler or Adreno GPU Profiler to analyze shader ALU/texture/bandwidth costs

- Implement AdaptiveQuality:

  - Monitor frame time via FrameTimingManager

  - If frame time exceeds 14 ms for 10 consecutive frames:

    - Reduce effect quality (halve blur passes, reduce kaleidoscope segments)

    - Reduce composite RT resolution (75% → 50%)

    - If still over budget, disable least-recently-added effect

  - If frame time drops below 10 ms for 30 frames, step quality back up

  - User can override: "Performance" vs. "Quality" mode in settings

Core Dev (Frame Budget Monitor):

- Implement on-screen debug overlay (dev builds only):

  - FPS counter, frame time graph, GPU time, draw calls, RT memory, GC allocs

  - Toggle via shake gesture or dev settings

- Implement PerformanceLogger: write frame timing data to file for offline analysis

UI/UX:

- Layer panel (right drawer):

  - Two layer cards showing thumbnail preview, media name, effect badges

  - Solo/mute/opacity controls per layer

  - Tap to select active layer (all tools operate on selected layer)

- Crossfade slider: horizontal slider at bottom of canvas, large thumb for easy grab

- Blend mode picker: dropdown on the mixer slider

- Performance indicator: subtle colored dot (green/yellow/red) in status bar

QA:

- Performance test matrix: all combinations of (no media / image / video) x (no effects / 1 effect / 2 effects) x (no drawing / drawing) across both layers

- Memory leak test: run app for 30 minutes with continuous layer switching and media loading

- Crossfade smoothness test: slide crossfader continuously for 60 seconds, check for dropped frames

- Test on lowest-tier target device (Snapdragon 695 class): verify adaptive quality kicks in appropriately

Edge Cases:

- Both layers playing video simultaneously: may exceed decode bandwidth on some devices; consider fallback to single-decoder mode

- Switching active layer while drawing: stroke must continue on new layer without artifact

- Layer with no content: render as transparent (not black) for proper compositing

- Blend mode with fully transparent layer: should have no visual effect (verify math)

Phase 5: Import/Export and Project System (Week 10)

Goal: Complete project persistence (save/load), media export, and the project browser.

Duration: 1 calendar week

Key Deliverables:

- Project save/load (all settings, warp state, masks, drawings, media references, effect configs)

- Project browser with thumbnails and metadata

- Video clip export (record composite output to MP4)

- Screenshot export (single frame PNG)

- Auto-save

Success Metrics:

- Save and reload a complex project (2 layers, warps, masks, drawings, effects) with perfect fidelity

- Project browser shows all saved projects with thumbnails, sorted by last modified

- Export a 10-second 1080p MP4 in under 30 seconds on mid-range device

- Auto-save triggers every 60 seconds without frame drop

Dependencies: Phases 1–4 complete

Detailed Task Breakdown:

Core Dev (Project System):

- Define ProjectData JSON schema:

{

"version": "1.0",

"name": "My Project",

"created": "2026-02-25T12:00:00Z",

"modified": "2026-02-25T14:30:00Z",

"resolution": { "width": 1920, "height": 1080 },

"layers": [

{

"id": "layer-a",

"media": { "type": "video", "path": "media/clip1.mp4", "startTime": 0, "loop": true },

"warp": { "type": "fourCorner", "corners": [[x,y],[x,y],[x,y],[x,y]] },

"mask": { "type": "polygon", "vertices": [[x,y],...], "inverted": false },

"drawing": { "texturePath": "drawings/layer-a.png" },

"effects": [

{ "type": "kaleidoscope", "params": { "segments": 8, "rotation": 0.5 } }

],

"opacity": 1.0,

"muted": false

}

],

"mixer": { "crossfade": 0.5, "blendMode": "normal" }

}

- Implement ProjectManager:

  - SaveProject(name): serialize all state to JSON, save drawing RTs as PNG, copy media to project folder, capture thumbnail

  - LoadProject(id): deserialize JSON, restore all state, reload media, rebuild meshes

  - DeleteProject(id): remove project folder

  - ListProjects(): enumerate project folders, return metadata + thumbnail paths

  - Projects stored in: Application.persistentDataPath/Projects/{guid}/

- Implement auto-save:

  - Timer-based (every 60 seconds) + event-based (on significant change)

  - Save to .autosave subfolder, rotate last 3 auto-saves

  - Must be non-blocking: serialize JSON on main thread (fast), save textures and files on background thread

  - Key gotcha: Texture2D.EncodeToPNG() must run on main thread; schedule via coroutine, spread across frames

Core Dev (Export):

- Implement ExportService:

  - Screenshot: ReadPixels from composite RT → Texture2D.EncodeToPNG → save to gallery via MediaStore API

  - Video Export: Use Unity Recorder package or custom AsyncGPUReadback + MediaCodec pipeline

    - Read composite RT each frame via AsyncGPUReadback.Request

    - Encode frames to H.264 via Android MediaCodec (hardware encoder)

    - Mux to MP4 via MediaMuxer

    - Target: 1080p @ 30 fps export (not 60 fps to keep file size reasonable)

    - Show progress bar with cancel option

  - Save exported files to Movies/Maptifier/ via MediaStore for gallery visibility

- Key gotcha: AsyncGPUReadback has a 2–3 frame latency; must buffer frames. Also not supported on OpenGL ES on some devices; fallback to ReadPixels (slower, causes stall)

UI/UX:

- Project browser screen:

  - Grid of project cards (thumbnail + name + last modified)

  - Create new project button (prominent)

  - Long-press for delete/duplicate/rename context menu

  - Search/filter (if 10+ projects)

- Export dialog: choose format (screenshot/video), resolution, duration (for video), destination

- Save confirmation toast, loading progress for project load

QA:

- Test save/load roundtrip fidelity: compare pixel-level output before save and after load

- Test with corrupt project JSON (truncated, invalid fields): app should show error, not crash

- Test export on devices with limited storage: handle gracefully

- Test auto-save during heavy rendering: verify no frame drops

- Test project with missing media files (deleted from gallery): show placeholder, don't crash

Edge Cases:

- Media file deleted from gallery after import: store copy in project folder, or show "media missing" placeholder on load

- Project saved on one device, loaded on another with different screen ratio: re-map warp coordinates proportionally

- Export while projecting: export should capture composite output, not phone preview (which may be letterboxed)

- Storage full during save: catch IOException, show user-friendly error, don't corrupt existing save

Phase 6: Polish, UI/UX and Onboarding (Weeks 11–12)

Goal: Bring the app to consumer quality — polished UI, onboarding, accessibility, and content.

Duration: 1.5 calendar weeks

Key Deliverables:

- Onboarding flow (first-launch tutorial)

- UI animations and transitions (panel slides, tool switches, toast notifications)

- Haptic feedback on key interactions

- Settings screen (display preferences, performance mode, about)

- 3–5 template projects (holiday themes, geometric, abstract)

- App icon and splash screen using approved logo

Success Metrics:

- New user completes onboarding and creates first projection in under 3 minutes

- All UI transitions are smooth (no jank)

- Settings changes apply immediately without restart

- Template projects load and render correctly on all test devices

- Splash screen displays correctly on all screen sizes

Dependencies: Phases 1–5 feature-complete

Detailed Task Breakdown:

UI/UX Designer + Dev:

- Onboarding flow (4–5 screens):

  - Welcome + branding (logo animation)

  - "Connect your projector" — show cable illustration, detect if already connected

  - "Import or draw" — quick demo of import and drawing

  - "Warp to fit" — show corner-drag animation

  - "You're ready!" — create first project

- Implement with UI Toolkit, swipe-to-advance, skip button

- Coach marks: contextual tooltips on first use of each tool ("Drag corners to fit your surface")

- UI polish:

  - Panel slide-in/out animations (200 ms ease-in-out)

  - Tool switch transitions (icon highlight animation)

  - Button press feedback (scale down 95% + haptic)

  - Toast notifications (slide up from bottom, auto-dismiss 3s)

- Haptic feedback: Handheld.Vibrate() is too crude; use Android VibrationEffect.createOneShot(10, 128) via native plugin for subtle taps

- Settings screen:

  - Display: resolution override, force display mode

  - Performance: Quality / Balanced / Performance mode

  - Drawing: default brush size, pressure sensitivity curve

  - About: version, licenses, feedback link

- Dark theme final polish: ensure all states (pressed, disabled, focused) are styled

Content Dev:

- Create 3–5 template projects:

  - "Geometric Pulse": kaleidoscope effect on geometric pattern, mesh-warped

  - "Holiday Lights": warm color cycle on star pattern, 4-corner warped

  - "Abstract Flow": wave distortion on gradient, drawing overlay

  - "Logo Spotlight": placeholder for user logo, tunnel effect, edge glow

- Templates stored as Addressable assets, loaded on first launch

- Template thumbnails for project browser

Core Dev:

- Implement splash screen: Unity splash (required for Personal license) + custom animated logo screen (1.5 seconds max)

- Generate app icon set from Maptifier-1.png: adaptive icon (foreground layer + background), round icon, legacy square

- Implement AnalyticsService (Firebase Analytics):

  - Events: app_open, project_created, project_loaded, media_imported, display_connected, export_completed, effect_applied, session_duration

  - No PII, respect GDPR (consent dialog if distributing in EU)

QA:

- Onboarding usability test: 3+ non-technical users complete onboarding, record success rate and pain points

- UI accessibility audit: contrast ratios (minimum 4.5:1 for text per WCAG AA), touch target sizes (minimum 48dp)

- Test all UI states: empty states, error states, loading states, overflow text

- Test templates on all devices in matrix

Phase 7: Testing, Optimization and Device Certification (Weeks 12–13)

Goal: Systematic testing, performance optimization, and certification across target device matrix.

Duration: 1.5 calendar weeks

Key Deliverables:

- Full test pass on 10+ devices across 3+ OEMs

- Performance optimization achieving 60 fps targets on all target devices

- Crash-free rate above 99.5% across 100+ test sessions

- Memory usage under hard limits (512 MB total, no OOM on 4 GB RAM devices)

- Battery usage optimization (no excessive drain when idle)

- Wireless display fallback (Cast/Miracast) — basic support

Success Metrics:

- All target devices (Snapdragon 7xx/8xx) sustain 60 fps with dual layers + 1 effect each

- No ANR (Application Not Responding) occurrences in 100 test sessions

- Cold start time under 3 seconds on mid-range devices

- Video export works on all tested devices

- Zero critical bugs, under 5 major bugs remaining

Dependencies: All feature phases complete (0–6)

Detailed Task Breakdown:

QA (Systematic Testing):

- Execute full test plan covering every feature on every device in matrix

- Device matrix (minimum):

  - Samsung Galaxy S23/S24 (Snapdragon 8 Gen 2/3) — flagship baseline

  - Samsung Galaxy A54/A55 (Exynos 1380/1480) — mid-range Samsung

  - Google Pixel 7a/8a (Tensor G2/G3) — mid-range Pixel

  - Xiaomi Redmi Note 12/13 Pro (Snapdragon 7s Gen 2) — mid-range Xiaomi

  - OnePlus Nord 3/4 (Dimensity 9000/8300) — MediaTek GPU variant

  - Samsung Galaxy Tab S9 (Snapdragon 8 Gen 2) — tablet form factor

- Test categories:

  - Functional: every feature works as specified

  - Performance: frame rate, memory, battery, thermal

  - Stress: 30-minute continuous use, rapid feature switching, 10+ project saves

  - Edge: airplane mode, low storage, low battery, accessibility mode (TalkBack), split-screen

  - External display: every device + every adapter combination

  - Lifecycle: home button, recent apps, phone call interruption, notification overlay, screen rotation lock

Graphics Dev (Optimization Pass):

- Profile every device using:

  - Unity Profiler (CPU frame time breakdown)

  - FrameTimingManager (GPU time)

  - Android GPU Inspector (Adreno) or ARM Streamline (Mali) for shader-level analysis

  - SystemInfo for GPU capability detection

- Optimize per-device:

  - Adreno GPUs: prefer half precision, avoid dependent texture reads, use Vulkan

  - Mali GPUs: minimize fragment shader complexity, avoid discard, prefer alpha test

  - PowerVR GPUs (rare but present): ensure tile-based deferred rendering compatibility

- Implement GPU capability tiers:

  - Tier 1 (flagship): full resolution, max effects, no compromises

  - Tier 2 (mid-range): 75% RT resolution, reduced blur passes, max 2 effects per layer

  - Tier 3 (low-end): 50% RT resolution, simplified effects, max 1 effect per layer

  - Tier detected on first launch via SystemInfo.graphicsMemorySize, SystemInfo.processorCount, benchmark test

Core Dev (Wireless Display Fallback):

- Implement Miracast/Google Cast detection via MediaRouter API

- Cast composite RT as a media route (this is significantly more complex than wired — treat as best-effort)

- Known limitation: Cast has 100–200 ms latency; show warning to user

- Test on Chromecast, Miracast-compatible TV, Samsung Smart View

Core Dev (Stability):

- Implement global exception handler: catch unhandled exceptions, log to Crashlytics, show "Something went wrong" dialog with retry/report options

- Implement ANR watchdog: monitor main thread responsiveness, log if approaching ANR threshold (5 seconds)

- Audit all async code for proper exception handling and cancellation

- Test with Android "Don't keep activities" developer option enabled

QA (Regression):

- Full regression pass after each optimization fix

- Automated screenshot comparison for visual regression (capture composite output, compare against baseline)

Phase 8: Release Preparation and Store Assets (Week 14)

Goal: Prepare everything needed for Play Store submission and successful launch.

Duration: 1 calendar week

Key Deliverables:

- Signed release APK/AAB (Android App Bundle)

- Play Store listing: screenshots, feature graphic, description, categorization

- Privacy policy and terms of service

- ProGuard/R8 rules for release build

- Pre-launch report (Firebase Test Lab)

- Launch checklist verified

Success Metrics:

- AAB passes Play Store pre-launch checks with no critical issues

- APK size under 100 MB (with Addressables for on-demand content)

- All store assets meet Play Store requirements (screenshot sizes, content rating)

- Privacy policy covers all data collection (analytics, crash reporting)

- App rated "Everyone" on IARC content rating

Dependencies: Phase 7 complete, all critical bugs fixed

Detailed Task Breakdown:

Core Dev (Release Build):

- Configure release signing keystore (store securely, NOT in repo)

- Set up ProGuard/R8 rules for Unity Android:

  - Keep rules for Unity internals, Firebase, any reflection-based code

  - Test release build thoroughly (R8 can break reflection/serialization)

- Enable AAB (Android App Bundle) + Play Asset Delivery for Addressables

  - Base APK: core app under 150 MB

  - On-demand: template projects, additional effects (install-time asset pack)

- Set version code and version name (1.0.0 / version code 1)

- Final IL2CPP build with Release configuration, stripping enabled (managed, engine code)

- Key gotcha: IL2CPP stripping can remove code accessed via reflection; use [Preserve] attribute or link.xml

UI/UX Designer (Store Assets):

- Screenshots: 5–8 screenshots showing key features:

  - External display connected, projecting onto surface

  - 4-corner warping in action

  - Drawing on canvas

  - Effects library

  - Dual-layer mixing

  - Project browser

  - Settings / onboarding

- Feature graphic: 1024x500 banner using logo + key visual

- App icon: 512x512 hi-res icon for store listing

- Short description (80 char): "Turn your Android phone into a pocket projection mapper"

- Full description: feature list, requirements, keywords

- Demo video: 30–60 second screen recording showing core workflow

Core Dev / PM:

- Content rating questionnaire (IARC)

- Privacy policy page (host on GitHub Pages or simple landing page):

  - Data collected: crash logs (Crashlytics), anonymous usage analytics (Firebase)

  - No PII, no user accounts, no ads

  - Data retention policy

- Target API level compliance check (SDK 34 required for new Play Store submissions in 2026)

- Run pre-launch report via Firebase Test Lab: automated crawl test on 10+ devices

- Review and fix any pre-launch report issues

QA (Final Validation):

- Install release AAB via bundletool on all test devices

- Full smoke test of every feature on release build

- Verify ProGuard/R8 hasn't broken anything (pay special attention to JSON serialization, shader loading)

- Verify no debug logs, no development watermarks, no placeholder content

- Verify analytics events fire correctly in release build

- Verify crash reporting works (intentionally trigger crash, verify it appears in Crashlytics)

4. Risks and Mitigations

R1: USB-C / DisplayPort Alt-Mode Fragmentation

- Likelihood: HIGH

- Impact: HIGH (core feature depends on it)

- Details: Not all USB-C ports support DisplayPort alt-mode. Samsung, Pixel, and OnePlus generally do on mid-range+. Xiaomi is inconsistent. Some phones support alt-mode but only with specific adapters. Samsung DeX mode hijacks the external display.

- Mitigations:

  - Test with 5+ adapter brands in Phase 0 spike

  - Maintain a known-compatible device/adapter list in docs and app FAQ

  - Detect DeX mode and show user guidance to disable it or work within it

  - Implement wireless Cast/Miracast as fallback in Phase 7

  - Clear in-app messaging when no display detected ("Connect via USB-C HDMI adapter or Cast to a supported device")

  - Consider supporting Samsung DeX natively (show app in windowed mode on external display) as v2 feature

R2: Mid-Range GPU Performance Under Full Load

- Likelihood: MEDIUM-HIGH

- Impact: HIGH (60 fps is a core promise)

- Details: Dual layers + 2 effects each + drawing + video decode + external display blit may exceed GPU budget on Snapdragon 7xx and Exynos 1380.

- Mitigations:

  - Strict frame budget monitoring from Phase 1 onward

  - Adaptive quality system (Phase 4) that degrades gracefully

  - Use half precision in all shaders, minimize texture samples

  - Limit effects per layer (hard cap of 3)

  - Use Dual Kawase blur instead of Gaussian (2x efficiency gain)

  - RT resolution scaling (render at 75% and upscale for mid-range, 50% for low-end)

  - Profile with Mali Offline Compiler and Adreno GPU Profiler during Phase 7

  - If needed: downgrade to 30 fps target for lowest-tier devices with clear user communication

R3: External Display Resolution Negotiation and VSync

- Likelihood: MEDIUM

- Impact: MEDIUM

- Details: External displays may report unusual resolutions, or support multiple modes. VSync between phone (e.g., 120 Hz) and external display (e.g., 60 Hz) can cause tearing or judder.

- Mitigations:

  - Always query Display.getSupportedModes() and select best match

  - Cap rendering to 60 fps regardless of phone display refresh rate

  - Use triple buffering on external surface to absorb timing differences

  - Allow user to manually select resolution in settings as override

  - Test with: 720p projector, 1080p monitor, 4K TV, ultrawide monitor

R4: Android Permissions and Background Behavior

- Likelihood: MEDIUM

- Impact: MEDIUM

- Details: Android 10+ scoped storage changes media access permissions. Android 12+ requires exact permission declarations. OEM battery optimizations (Xiaomi, Huawei, Samsung) can kill the app while projecting. Android 14 changes foreground service requirements.

- Mitigations:

  - Use READ_MEDIA_IMAGES and READ_MEDIA_VIDEO (SDK 33+) instead of READ_EXTERNAL_STORAGE

  - Request FOREGROUND_SERVICE_MEDIA_PROJECTION for external display rendering

  - Use WakeLock + FLAG_KEEP_SCREEN_ON to prevent sleep during projection

  - Guide users to disable battery optimization for Maptifier on first launch

  - Test on MIUI, One UI, ColorOS specifically for battery optimization behavior

  - Implement ForegroundService with persistent notification during active projection

R5: Fluid Drawing Feel Across Devices

- Likelihood: MEDIUM

- Impact: MEDIUM (affects creative tool quality)

- Details: Touch digitizer sample rate, pressure support, and palm rejection vary wildly across devices. Some devices report touch at 60 Hz, others at 240 Hz. Not all report pressure.

- Mitigations:

  - Use velocity-based pressure simulation as default, with device pressure as opt-in enhancement

  - Implement touch prediction (extrapolate next point position based on velocity) to reduce perceived latency

  - Adaptive spline subdivision based on input rate (more subdivision for lower-rate devices)

  - Test with Samsung S Pen (true pressure), Pixel (no stylus), and third-party capacitive stylus

  - Provide sensitivity/smoothing controls in settings

R6: Video Decode Performance for Dual-Layer Video

- Likelihood: MEDIUM

- Impact: MEDIUM

- Details: Running two simultaneous hardware video decoders is not guaranteed on all devices. MediaCodec typically supports 1–3 concurrent decode instances depending on SoC.

- Mitigations:

  - Detect concurrent decoder limit via MediaCodecList on startup

  - If only 1 decoder available: allow video on one layer only, show warning on second

  - Use software decode (slower, lower res) as fallback for second video

  - Prefer image sources for one layer when dual-video is unsupported

R7: App Bundle Size

- Likelihood: LOW-MEDIUM

- Impact: LOW-MEDIUM

- Details: Unity apps tend to be large (100 MB+). Shader variants, URP assets, templates, and textures add up.

- Mitigations:

  - Aggressive shader variant stripping (can save 30–50 MB)

  - Use Play Asset Delivery for templates and on-demand content

  - Compress all textures with ASTC (Android-optimal format)

  - Target base APK under 80 MB, total with asset packs under 150 MB

  - Audit asset sizes weekly during development

5. Team Roles and Suggested Jira Epic Structure

Team Roles

- Core Dev Lead (1): Architecture, project system, external display, input system, build pipeline, Android native plugins. Also serves as tech lead for code reviews and architecture decisions.

- Graphics/Shader Dev (1–2): Warp engine, mask engine, drawing engine, all effects shaders, URP customization, performance profiling. This is the most specialized role — needs strong shader programming experience.

- UI/UX Dev (1): UI Toolkit implementation, onboarding, animations, settings. Works closely with designer.

- UI/UX Designer (1): Wireframes, style guide, store assets, onboarding flow, template content. Can be part-time after Phase 1.

- QA Engineer (1): Device testing, performance testing, regression, store submission testing. Ramps up from Phase 2 onward.

Jira Epic Structure

- MAPT-SETUP: Project Setup and Spikes (Phase 0)

- MAPT-DISPLAY: External Display Pipeline (Phase 1)

- MAPT-INPUT: Input System and Gestures (Phase 1)

- MAPT-MEDIA: Media Import Pipeline (Phase 2)

- MAPT-WARP: Warp Engine (Phase 2)

- MAPT-MASK: Mask Engine (Phase 2)

- MAPT-DRAW: Drawing Engine (Phase 3)

- MAPT-FX: Effects Pipeline and Library (Phase 3)

- MAPT-LAYERS: Layer System and Mixing (Phase 4)

- MAPT-PERF: Performance Optimization (Phase 4, 7)

- MAPT-PROJECT: Project Save/Load/Export (Phase 5)

- MAPT-UI: UI Shell, Polish, and Onboarding (Phase 1, 6)

- MAPT-CONTENT: Templates and Store Assets (Phase 6, 8)

- MAPT-QA: Testing and Device Certification (Phase 7)

- MAPT-RELEASE: Release Preparation (Phase 8)

Each epic contains stories broken down into tasks. Use story points (Fibonacci: 1, 2, 3, 5, 8, 13) for estimation. Two-week sprints aligned with phases.

6. Milestones and Demo Cadence

Weekly Friday Demos

| Week | Demo Content |
| --- | --- |
| Week 1 (Phase 0) | Spike results: external display showing test pattern, video playing on RT, touch strokes rendering. CI building APKs. |
| Week 2 (Phase 1a) | External display connected and showing a solid color/test image. Hot-plug works. Gesture system demo (pinch/pan on canvas). |
| Week 3 (Phase 1b) | Full display pipeline: RT renders on phone AND external display. Dark UI shell with tool bar. Input coordinate mapping works. |
| Week 4 (Phase 2a) | Import a photo from gallery, display on canvas. 4-corner warp with draggable handles, output to projector. |
| Week 5 (Phase 2b) | Video import working. Mesh warp (4x4 grid). Polygon and brush masking functional. Full warp+mask pipeline on projector. |
| Week 6 (Phase 3a) | Drawing engine demo: free draw on canvas with pressure simulation, color picker, brush size. 3–4 effects working. |
| Week 7 (Phase 3b) | Full effects library (5–8 effects). Effect parameter UI. Effects + drawing + media composited together. |
| Week 8 (Phase 4) | Dual layers with crossfade mixing. Blend modes. Performance overlay showing 60 fps. Adaptive quality demo. |
| Week 9 (Phase 5) | Project save and reload demo. Export a 10-second video clip. Project browser with thumbnails. |
| Week 10 (Phase 6a) | Onboarding flow. UI animations. Template projects. Settings screen. |
| Week 11 (Phase 6b) | Full polish pass. Haptic feedback. App icon and splash. Coach marks. |
| Week 12 (Phase 7a) | Device matrix test results. Performance numbers across all devices. Wireless display demo (if ready). |
| Week 13 (Phase 7b) | All critical bugs fixed. Stability metrics. Pre-launch report results. |
| Week 14 (Phase 8) | Release candidate AAB. Store listing preview. Final sign-off demo. |

Key Milestones

- M1 (End of Week 3): "First Light" — content visible on external projector via the app

- M2 (End of Week 5): "Core Loop" — import media, warp it, mask it, see it on projector (MVP core)

- M3 (End of Week 7): "Creative Suite" — drawing + effects fully functional

- M4 (End of Week 9): "Feature Complete" — all MVP features working (MVP candidate)

- M5 (End of Week 11): "Consumer Ready" — polished UI, onboarding, templates

- M6 (End of Week 14): "Gold Master" — Play Store submission

7. Recommended Next Immediate Actions (First 48–72 Hours)

Hour 0–8: Environment Setup

- Create GitHub repository maptifier-android with branch protection on main, require PR reviews

- Install Unity 6 LTS (2025.3.x) on all dev machines via Unity Hub; verify Android Build Support module

- Create Unity project with URP template, configure for Android (ARM64, IL2CPP, Vulkan + GLES 3.2 fallback)

- Set up Git LFS tracking rules and commit initial project

- Configure GitHub Actions CI to build debug APK on push to develop

Hour 8–16: Spike Preparation

- Order 3 different USB-C to HDMI adapters (different chipsets: Analogix, Parade, ITE) if not already available

- Assign spike owners: Dev A → External Display, Dev B → Video Pipeline, Dev C → Drawing Latency

- Each spike owner creates a branch, writes a minimal test scene, targets 1-day turnaround

Hour 16–32: Spike Execution

- External Display spike: write Android Presentation plugin, test on Samsung + Pixel + one other device

- Video spike: play 1080p H.264 to RenderTexture, measure perf on mid-range device

- Drawing spike: capture touch, render Catmull-Rom strokes, measure latency

Hour 32–48: Alignment

- Review spike results as a team — document findings, identify any showstoppers

- If external display spike fails on a target device: document workaround or adjust device matrix

- UI/UX designer delivers initial style guide and wireframes for Canvas View

- Populate Jira board with Phase 0 and Phase 1 stories

- QA sets up device matrix spreadsheet and Firebase project (Crashlytics + Analytics)

Hour 48–72: Phase 0 Wrap-Up

- Merge all spike branches into develop

- Code review spikes, extract reusable patterns into production architecture

- Finalize folder structure, assembly definitions, coding standards doc

- Team alignment meeting: review roadmap, confirm Phase 1 assignments, address concerns

- First CI-built APK installed and running on all test devices — "Hello Projector" moment